## Description
Scenario Quality Checker (SQC)
For analysts documenting functional requirements with scenarios, our SQC application will provide quantitative information and enable detection of problems in functional requirements written in the form of scenarios. The application will be available via GUI and also as a remote API, thanks to which it can be integrated with existing tools.
Format of scenarios to be put into the Readme.md project: • The scenario includes a header specifying its title and actors (external and system) • The scenario consists of steps (each step contains text) • Steps can contain sub-scenarios (any level of nesting) • The steps may start with the keywords IF, ELSE, FOR EACH Example: Title: Book addition Actors: Librarian System actor: System • Librarian selects options to add a new book item • A form is displayed. • Librarian provides the details of the book. • IF: Librarian wishes to add copies of the book o Librarian chooses to define instances o System presents defined instances o FOR EACH: instance: • Librarian chooses to add an instance • System prompts to enter the instance details • Librarian enters the instance details and confirms them. • System informs about the correct addition of an instance and presents the updated list of instances. • Librarian confirms book addition. • System informs about the correct addition of the book.

## Product Backlog
Product Backlog item | Importance | Labour intensity | Business Value (BV) | Acceptance Criteria
As a developer of analyst tools, I can use the available functions remotely via REST to be able to integrate the tool with my other applications | 20 | 7 | 1 | o Input in JSON format corresponding to the structure of a scenario (dictionaries, lists) o Input transformed into an object model (scenario, step, ...) o Output in JSON format o REST API allows you to run any currently implemented function.
As an analyst, I can check how many steps the entire scenario (including sub-scenarios) contains to assess how complicated it is | 15 | 5 | 1 | o Empty scenario -> 0 steps o Number of scenario steps = Number of scenario steps + number of steps in all its direct and indirect sub-scenarios
As an analyst, I can check how many steps contain keywords to find out how many conditional decisions are in the scenario | 12 | 3 | 1 | o Each step in the structure starting with keywords increments the result by one o A scenario without steps starting with keywords yields a result of zero
As an analyst, I can see which steps do not start with the actor performing the action in order to correct this type of error | 10 | 5 | 1 | o For a scenario where all steps start with the actor name (keywords are ignored) the result is an empty list o In the event that any of the steps (at any level of depth) does not start with an actor (omitting keywords), all such steps must be returned as a list
As an analyst, I can download the scenario as a text with step numbers for inclusion in the documentation | 10 | 3 | 1.5 | o Each subsequent step on a given level is incremented by one number, starting with one and ending with a period (e.g. 1. 2. ...) o Numbers on successive levels of nesting are created by copying the number of the "parent" and assigning the numbering at a given level (eg 4.3.).
As an analyst, I can obtain a scenario containing only sub-scenarios up to a certain level to present a simplified version of the requirements | 10 | 5 | 1 | o The input contains the scenario structure and the level number o For level = 1, only the top-level scenario is returned o For levels> 1, scenarios up to and including the level are returned (e.g. level = 2 means the scenario at the highest level and its direct sub-scenarios)
As a user, I can utilise the application via the user interface. | 20 | 7 | 1.5 | o Scenario can be created, edited and displayed o Ability to send request to REST API o Output is displayed to the user

## Sprint #1 Backlog
Sprint Goal: Achieve 6.5 BV
Product Backlog Item | Tasks | Labour intensity
General Setup & DoD
| Create the initial project structure and push to the repository. | 0.5
| Configure the Continuous Integration (CI) | 0.5
| Create and configure Github Issues | 1
| Creating a UML diagram | 8
| Implement logging using SL4J library | 2
As a developer of analyst tools, I can use the available functions remotely via REST to be able to integrate the tool with my other applications |  | 7
| Design JSON schema | 2
| Implement REST API endpoints | 2
| Implement Object Model of a scenario (visitor pattern) | 1.5
| Implement JSON to Object Model transformation | 1.5
As an analyst, I can check how many steps the entire scenario (including sub-scenarios) contains to assess how complicated it is |  | 5
| Implement recursive logic for scenario/sub-scenario step counting using Visitor pattern | 4
| Implement sending JSON with response | 1
As an analyst, I can check how many steps contain keywords to find out how many conditional decisions are in the scenario |  | 3
| Implement keyword detection logic for conditional decisions | 1
| Implement keyword counter into the main analysis tool | 1
| Implement sending JSON with response | 1
As an analyst, I can see which steps do not start with the actor performing the action in order to correct this type of error |  | 5
| Implement logic to ignore keywords and check for actor name presence | 2
| Develop a collector function to return a list of non-compliant steps | 2
| Implement sending JSON with response | 1
As an analyst, I can download the scenario as a text with step numbers for inclusion in the documentation |  | 3
| Implement a numbering algorithm for nested levels (e.g., 1., 1.1., 1.1.1.) | 2
| Create the file export/download utility for .txt output | 1
As an analyst, I can obtain a scenario containing only sub-scenarios up to a certain level to present a simplified version of the requirements |  | 5
| Implement logic to prune the scenario tree at a specified depth level | 2
| Develop the filtering service to return partial scenario structures | 2
| Implement sending JSON with response | 1

## Sprint #2 Backlog
Sprint Goal: Achieve 8 BV
Product Backlog Item | Tasks | Labour intensity
As a user, I can utilise the application via the user interface. |  | 7
| Implement creating a scenario | 1
| Implement editing a scenario | 1
| Implement displaying a scenario | 1
| Implement sending requests to REST API | 2
| Implement displaying output | 2